## NFT- RA
[5 empty] | Date | 2022-11-16
[5 empty] | Team ID | PNT2022TMID27071
[5 empty] | Project Name | Project - Gas Leakage Monitoring and Alerting system for Industries.
NFT - Risk Assessment
S.No | Scenario Name | Scope/feature | Functional Changes | Hardware Changes | Software Changes | Impact of Downtime | Load/Volume Changes | Risk Score
1 | Detection accuracy - Response | New | Low | Moderate | Moderate | No | No Changes | ORANGE
2 | Smoke above threshold limit | New | Moderate | No | No | Low | No Changes | GREEN
NFT - Detailed Test Plan
|  |  | S.No | Scenario name | NFT Test approach | Assumptions/Dependencies/Risks | Approvals/SignOff
|  |  | 1 | Detection accuracy - Response | Using Python and NodeRed | Dependency : Cloud client/Risk - Moderate
|  |  | 2 | Smoke above threshold limit | Using Python and NodeRed | Dependency : Cloud client/Risk - Low
End Of Test Report
S.No | Scenario name | NFT Test approach | NFR - Met | Test Outcome | GO/NO-GO decision | Identified Defects (Detected/Closed/Open) | Approvals/SignOff
1 | Detection accuracy - Response | Using Python and NodeRed | No | Expectaions partially met | NO-GO | Observed intermittent performance issue sometimes . Bug is open.
2 | Smoke above threshold limit | Using Python and NodeRed | Yes | Expectations met | GO | Oberved response for the leakage detection in the UI and its accuracy is as expected.

## DTP
NFT Test approach
Load Test

## Testdata (hidden)
New | No Changes | No Changes | RED | In-Scope | Baseline Test Approach
Existing | Low | >5 to 10% | ORANGE | Out of Scope | Benchmark Test Approach
| Moderate | >10 to 30% | GREEN
| High | >30 to 50 %
>50 to 70%
>70 to 100%